ACTION TRACKER April 21 meeting with Andrea + Garrett — all action items 9 actions tracked · 4 commitments from Andrea · Week-by-week ownership + status

ACTIONS WE OWN · Velocity GTM deliverables

| # | ACTION | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| 1 | Priority swap in all artifacts Clean swap: old P2 (7 displacement/greenfield targets) becomes new P1 — active focus. Old P1 (BELFOR, Evive, Threshold) becomes new P2 — existing footprint to protect and expand. | Michael | Fri Apr 24 | ✅ DONE · Dashboard v5 |
| 2 | P1 engagement readiness — research then build Two-phase work. Phase 1 (before 4/29): Research each P1 franchisor + brand for FSM platform status (mandate, preferred vendor, mixed, greenfield, unknown) AND estimated % of franchisees on paper/spreadsheet. Paper-based greenfield franchisees may warrant higher prioritization given cleaner ROI story and faster sales cycles — surface this as a potential priority change to discuss with Andrea and Garrett at 4/29. Phase 2 (post 4/29): Build P1 readiness document with 4-dimensional scoring (Awareness + PE/Scale + Warm Path + FSM Greenfield) and, if agreed at 4/29, propose Dashboard re-ranking. Target delivery: May 5. | Michael | May 5 | ⏳ PENDING · Research phase |
| 3 | Reactivation strategy — dormant and lost accounts Look at the SB customer base to identify dormant and lost accounts where we can reach back out. Goal is to build a structured reactivation playbook: which accounts are candidates, what changed since they left (new features, pricing, leadership), and what messaging brings them back. USA Insulation is the catalyst; the opportunity is broader. | Michael | May 6 | ⏳ PENDING |
| 4 | PitchBook data request spreadsheet All 11 franchisors × 37 data points organized by priority (P1 must-have / P2 should-have / P3 nice-to-have). For GPSI/ServiceBridge to send to Accel-KKR as a backup if direct PitchBook access isn't granted. | Michael | Before 4/29 | ✅ DONE |
| 5 | Track 3 formalization Formalize the 20+ location single-brand franchisor tier (Glass Guru, A-1 Concrete, A All Animal Control). Lighter-touch motion for franchisors already in SB footprint organically. | Michael | May 6 | ⏳ PENDING |
| 6 | Financing impact on franchisee revenue and profit Franchisor financing (e.g., GreenSky) is a profit lever to bake into every narrative and enablement asset. Three things to quantify: (1) average additional revenue per job when financing is offered, (2) what % of franchisee business is financed today across our Track 1 targets, (3) how we help franchisors improve both metrics. Work to be done collaboratively with internal GPSI people — need to identify the right contacts (finance, product, customer success). This becomes a standing talk track in pitches, not a one-time research item. | Michael + GPSI (TBD) | Owner TBD | ⏳ PENDING · Finding owner |
| 7 | Government + Public sector investigation Investigate fleet vehicle opportunities for GPSI + ServiceBridge in public and federal sectors. Scope work: understand GPSI's current gov footprint, research market opportunity, identify where SB+GPSI combined value lands. Independent desk research + conversations within GPSI. Build framing doc that lays out the opportunity space before any external outreach. | Michael | May 6 | ⏳ PENDING |
| 8 | CRM v18 update Align Prioritization tab + Track 1 Franchisors tab in ServiceBridge Master CRM to reflect priority swap. Low-complexity formatting update. | Michael | Before 4/29 | ⏳ PENDING |
| 9 | ServiceTitan pricing structure investigation Jack (Blanton’s technician) believes ServiceTitan may have recently moved to à la carte feature pricing. Verify: is this a real structural change, or Jack’s perception of the existing Starter/Essentials/Works + Pro add-on model? Materially affects our ServiceTitan displacement narrative. If pricing model has changed, update Blanton’s sizing and all future ServiceTitan-customer profiles accordingly. | Michael | Before 4/29 | ⏳ PENDING |

ACTIONS ANDREA OWNS · Inputs to our work

| # | COMMITMENT | OWNER | DUE | STATUS |
| --- | --- | --- | --- | --- |
| A1 | Jake Brown + Jason Perez — introduction Andrea to introduce Michael to Jake Brown and Jason Perez. Once the intro is made, Michael takes lead on setting up the meeting. Goal: deep SB client knowledge (won, lost, never-won) as critical input for Track 2 prioritization and historical SB context. | Andrea (intro) | TBD | ⏳ Intro pending |
| A2 | Internal systems access + intros Access to GPSI/SB internal systems for Michael. Introductions to relevant sellers and data people. Review progress at 4/29 meeting. | Andrea | EOD this week | ⏳ In progress |
| A3 | Accel-KKR PitchBook engagement Engage Accel-KKR contacts for direct PitchBook access. Fallback: use the data request spreadsheet we delivered. | Andrea | In progress | ⏳ In progress |
| A4 | ICP definition for ServiceBridge Andrea to share the ideal customer profile directly or connect Michael to the right person who owns it. Michael then maps Track 1 / 2 / 3 against the ICP. Review at 4/29 meeting. | Andrea (deliver or connect) | Next week | ⏳ Pending |

APRIL 29 MEETING AGENDA · What to review with Andrea + Garrett Next review checkpoint — topics to walk through together.

| TOPIC | WHAT TO COVER |
| --- | --- |
| 1. Priority 1 Franchisors — FSM status + potential priority change | Walk through what we've researched on each of the 7 P1 franchisors: FSM platform status per brand (ServiceTitan mandates, preferred vendors, greenfield). Surface a specific question: should paper-based franchisee populations drive higher priority given cleaner ROI story and faster sales cycles? Possible re-ranking decision to discuss. Andrea's team helps fill remaining gaps so we can build the P1 engagement readiness document (May 5 delivery). |
| 2. Reactivation strategy | Progress on the dormant and lost accounts review. Candidate list, messaging approach, and proposed reach-back playbook. Full scope doc by ~May 6. |
| 3. Internal systems access review | Confirm access granted + intros made. Any sellers Michael should connect with first? Angie specifically (micro-franchise list). |
| 4. ICP mapping | Andrea walks through the ServiceBridge ICP. Michael will map Track 1 / 2 / 3 franchisors against it and report back. |
| 5. Financing impact — revenue & profit lever | Need help identifying the right internal GPSI contacts (finance, product, customer success) to work with on this. Target metrics: avg revenue uplift per financed job, % of franchisee business financed, how SB/GPSI help improve both. Standing narrative thread, not one-time. |
| 6. PitchBook status | Did Accel-KKR come back on direct access? If not, walk through the data spreadsheet Andrea will send them. |
| 7. Forward look — May 6 deliverables | Preview: Two workstreams landing May 6 — Reactivation playbook (dormant + lost accounts) and Track 3 formalization (20+ location single-brand franchisors). No action needed at 4/29 beyond awareness. |
| 8. Open items + next cadence | Any new actions. Confirm next meeting cadence (weekly Wed?). |

STATUS SUMMARY Done: 2 of 9 actions complete (Priority swap → Dashboard v5 + Sources refresh, PitchBook data request spreadsheet). Pending (our side): 7 actions — P1 engagement readiness (research phase before 4/29, document delivery May 5), Reactivation strategy for dormant/lost accounts (May 6), Track 3 formalization (May 6), Financing impact research (collaborative with GPSI — finding owner), Government desk research (May 6), CRM v18 (before 4/29), ServiceTitan pricing structure investigation (before 4/29). Pending (Andrea): 4 commitments — Jake + Jason intro scheduled, internal systems access, Accel-KKR engagement, ICP definition. Focus areas since meeting: P1 engagement readiness is the headline for 4/29 — review what we’ve learned about each of the 7 P1 franchisors and identify which one is ready first. Reactivation strategy focused on dormant and lost accounts (May 6). Financing research reframed as collaborative with internal GPSI contacts to be identified. Government workstream scoped as independent desk research — no external outreach yet.